## Phase1
Identifying Test Environment(Phase1)
Application | PetStore | Collect Details From
URL | https://petstore.octoperf.com/actions/Catalog.action | BA, Functional Team, Dev

## Phase2
Identify Performance Metrics(Phase2)
|  | SLA(SEC) | Collect from: BA/ Business
Response Time | Min | <0.5
| Avg | <1.0
| Max | <2.0
| 90th Percentile | <1.5
| 95th Percentile | <1.8
Hlts/Sec | Throughput

## Phase3
| Plan and Design Performance Tests | Collect from: BA/ Business
In Scope: |  |  |  | 300 users percentage | 300 users | Complexity | Effort in Days
Web Application | Scenario 1 | Shopping Fish | Login Details | 20 | 30 | Medium | 2
Web Application | Scenario 2 | Shopping Dog | Login Details | 10 | 30 | Medium | 2
Web Application | Scenario 3 | Shopping Reptiles | Login Details | 10 | 15 | Medium | 2
Web Application | Scenario 4 | Shopping Cats | Login Details | 20 | 15 | Medium | 2
Web Application | Scenario 5 | Shopping Birds | Login Details | 10 | 15 | Medium | 2
Web Application | Scenario 6 | Login & Logout | Login Details | 20 | 15 | Medium | 2
Web Application | Scenario 7 | Add to Cart | Login Details | 10 | 120 | Medium | 2
Api | Scenario 8 | Search |  | 100 | 60
|  |  |  | No.of Testers=2 |  | Total Efforts by 2 TESTERS | 8 DAYS+2DAYS BUFFER
Web Application | Scenario1 | Shopping Fish
Step# | Transactions | Test data required | Assertion
Step1 | Enter the store | https://petstore.octoperf.com/actions/Catalog.action | Fish
Step2 | Click on sign in |  | Please enter username and password
Step3 | Enter the credentilas and login | Username and Password | My Account
Step4 | Click Fish |  | AngelFish
Step5 | Click on product | Item is FI-SW-01 | FI-SW-01
Step6 | Click on add to cart | Quantity must be random number | Shopping cart
Step7 | Click on proceed to checkout |  | Payment details
Step8 | Enter payment details and click continue | Test Payment card data & Address | Please confirm the information below and then press continue…
Step9 | Click on confirm |  | Shopping cart
Step10 | SignOut |  | Sign in
Api Call
URL | https://petstore.octoperf.com/actions/Catalog.action
Method | Post
Testdata | Fish/Dog/Reptiles
App Servers | App01 | App02
Web Servers | Web01
SQL Servers | SQL01
Firewall | Firewall01
Load Generators | Load01 | Load2
Smoke Test
Scenario 1:
Load Test | 100 Users / 1hr | 150 Users / 1 hr | 200 Users / 1hr
Soak Test | 40 Users/8hr | 60 Users/8hr | 80 Users/8hr | Ramp up/Ramp down | 10 min | 4 min/6min
Spike Test | 10 users/10 min
10 users/10 min
Scenario 2:
Load Test
Soak Test
Spike Test
12000
| Response Time | Think Time | Pacing
API 1 | 1 | 20 | 10
Post/Get |  |  | 1 users in 1 hr | 31 sec
|  |  | 10 users | 116.129
|  |  | 100 users | 1161.2903
11612.9032
Transaction 1
ThinkTime
Transaction2
ThinkTime
Transacion3
ThinkTime
Transacion4
Pacing
Load Test Dates | Monday | Tuesday
Soak Test Dates |  |  | Wednesday
Spike Test Dates |  |  |  | Thursday
Friday
Saturday
Out of Scope:
Security Testing
Functional Testing
UAT
Operational acceptance testing

## Phase 4
Configuring the test environment(Phase 4)
To be done before testing starts

## Phase 5
Implementing Test Design (Phase 5)
|  | Tested By | Integration Testing | Smoke Test
Scenario 1 | Completed | Sagar | Done | Done
Scenario 2 | Completed | Sagar | Done | Done
Scenario 3 | Completed | Sagar | Done | Done
Scenario 4 | Completed | Sagar | Done | Done
Scenario 5 | Completed | Sagar | Done | Done
Scenario 6 | Completed | Sagar | Done | Done
Scenario 7 | Completed | Sagar | Done | Done
Scenario 8 | Completed | Sagar | Done | Done
Step3 | username | sagar
| password | sagar
Step 5 | productId | FI-SW-01 | FI-SW-02 | FI-FW-01 | FI-FW-02
Step 6 | Working item id | EST-1, EST-2 | EST-3 | EST-4, EST-5 | EST-20,EST-21

## Phase 6
Execute the test (Phase6)
Executed in the project

## Phase 7
Analyze Report and Retest(Phase 7)
To be done with full load